## Sheet1
ACTIVITY | PREDECESSOR | ESTIMATED DURATION | EARLIEST |  | LATEST |  | SLACK
|  |  | START | FINISH | START | FINISH
Identify the Project Manager | - | 1 | 0 | 1 | 24 | 25 | 24
Create the Project Team | 1 | 2 | 1 | 3 | 27 | 29 | 26
Create the Project Charter | 2 | 4 | 3 | 7 | 25 | 29 | 22
Collecting the Project Requirements | 2, 3 | 10 | 7 | 17 | 29 | 39 | 22
Initiate Brainstorming Ideas | 4 | 1 | 17 | 18 | 39 | 40 | 22
Organize and Conduct Surveys | 5 | 5 | 18 | 23 | 40 | 45 | 22
Organize and Conduct Interviews | 6 | 3 | 23 | 26 | 45 | 48 | 22
Create the Project Scope Statement | 7 | 5 | 26 | 31 | 48 | 53 | 22
Plan and Create the Work Breakdown Structure | 8 | 5 | 31 | 36 | 53 | 58 | 22
Plan the Schedule of the Project | 9 | 5 | 36 | 41 | 58 | 63 | 22
Create an estimate of the Project Cost and Budget | 10 | 3 | 41 | 44 | 63 | 66 | 22
Purchase the Hardware Equipment | 11 | 4 | 44 | 48 | 66 | 70 | 22
Develop the Mobile Application | 12 | 1 | 48 | 49 | 70 | 71 | 22
Create the Homepage according to Houston Downtown Layout | 13 | 4 | 49 | 53 | 71 | 75 | 22
Create the Area Selection Page | 13 | 2 | 49 | 51 | 73 | 75 | 24
Create the Number Availability Page | 13 | 2 | 49 | 51 | 73 | 75 | 24
Create the Parking Satellite Image Page | 13 | 2 | 49 | 51 | 73 | 75 | 24
Create the Users Recommendations Page | 13 | 2 | 49 | 51 | 73 | 75 | 24
Link the Parking Sensor to Mobile Application | 13 | 2 | 49 | 51 | 73 | 75 | 24
Testing the Application | 14,15,16,17,18,19 | 15 | 53 | 68 | 75 | 90 | 22
Launch the Mobile Application | 20 | 10 | 68 | 78 | 90 | 100 | 22